## Onboarding
One row per task. Owner and due date are not optional.
Week | Task | Owner | Due | Depends on | Done
1 | Internal handover: sales walks delivery through what was sold | Sales | Day 1 | —
1 | Confirm scope against the signed document, not the pitch | Delivery lead | Day 2 | Handover
1 | Name the client-side decision maker and the day-to-day contact | Account manager | Day 2 | —
1 | Send the kickoff agenda before the kickoff | Account manager | Day 3 | Scope confirmed
2 | Kickoff call: agree the definition of done | Delivery lead | Day 6 | Agenda sent
2 | Access and credentials requested in writing | Delivery lead | Day 7 | Kickoff
2 | Set the reporting rhythm and who receives it | Account manager | Day 8 | Kickoff
3 | First deliverable, however small, in front of the client | Delivery | Day 12 | Access
3 | Raise anything already out of scope | Delivery lead | Day 14 | First deliverable
4 | Check in with the decision maker, not only the contact | Account manager | Day 20 | —
4 | Confirm invoicing schedule matches what was sold | Finance | Day 21 | Scope confirmed
Week one is internal. Onboarding that starts at the kickoff has already lost a week.