## Checklist
In order. The order is what stops the expensive surprises.
# | Stage | Task | Why | Done
1 | Before | Agree the stage names in the new system | Renaming stages after import means re-mapping every deal
2 | Before | Export a full copy of the old system and keep it | The rollback plan is a file, not an intention
3 | Before | List custom fields and decide which survive | Half of them are somebody’s abandoned experiment
4 | Before | Decide how much history comes across | Three years is enough for almost everyone
5 | Export | Companies and contacts, with the link between them | Contacts imported without their company are the classic loss
6 | Export | Open deals, with owner, stage, value and close date
7 | Export | Closed-won and closed-lost, with dates | Without these the forecast has no baseline for months
8 | Export | Activity and notes, at least for open deals | This is the second thing that always gets dropped
9 | Import | Load into a sandbox first, never straight to live
10 | Import | Check five records by hand against the old system | Row counts match while fields are silently empty
11 | Import | Re-point integrations and forms one at a time
12 | Switch | Run both systems for one full week
13 | Switch | Make the old system read-only rather than deleting it
14 | Switch | Tell everyone the date the old one goes away
Tasks 7 and 8 are the ones people skip and then miss for a year.