## Summary
Fill this in within two working days, while people still remember.
Field | Value
Incident | [Short name]
Date | [When]
Severity | [Sev 1–4]
Duration | [Detection to resolution]
Customers affected | [Number or proportion]
What broke | [One sentence, no jargon]
Detected by | [Monitoring, or a customer — this matters]
Author | [Name]
"Detected by: a customer" is the most useful line in the document.

## Timeline
One row per event. Times, not adjectives.
Time | Event | Who
[09:14] | [First error in logs]
[09:41] | [Customer reports it]
[09:52] | [Acknowledged, investigation starts]
[10:20] | [Cause identified]
[10:35] | [Fix deployed]
[11:00] | [Confirmed resolved]
The gap between the first log line and the acknowledgement is usually the finding.

## Causes and actions
Causes are conditions, not people. Every action has an owner and a date.
Contributing cause | Action | Owner | Due | Done
[What made this possible] | [The change that prevents it]
[What delayed detection] | [The alert that would have caught it]
[What delayed the fix] | [The runbook or access that was missing]
A postmortem with no dated actions is a story. Three owned actions beat ten unowned ones.