## Plan
One primary measure for the month. Everything else serves it.
Field | Value
Month | [Month]
Primary measure | [Non-brand clicks / ranked keywords / sourced pipeline]
Starting value | [Number from the last day of last month]
Target | [The value that counts as a good month]
Owner | [Name]
Biggest constraint | [What will stop this, named now]
One measure. Reporting three means reporting whichever moved.

## Work
What you will actually do. Effort in days, not adjectives.
Item | Type | Effort (d) | Expected effect | Owner | Status
Fix the 12 orphan feature pages | Technical | 1 | Indexing, then long-tail clicks |  | Planned
Rewrite 20 duplicate titles | On-page | 1 | Click-through on existing rankings |  | Planned
Publish two guides on head terms | Content | 5 | New rankings in 8–12 weeks |  | Planned
Internal links to the 15 deepest pages | On-page | 1 | Crawl depth and ranking |  | Planned
Content effects arrive in months; technical fixes arrive in weeks. Plan a mix or the month looks empty.