## Checklist
Do not skip the before stage. It is the only one that cannot be done later.
# | Stage | Task | Why | Done
1 | Before | Export every current URL with its traffic and rankings | This is the baseline; without it you cannot prove what broke
2 | Before | Export current titles, descriptions and H1s
3 | Before | Build the redirect map: every old URL to exactly one new URL | The map is the deliverable, not an afterthought
4 | Before | Check the map for chains and loops | A redirect to a redirect loses signal at every hop
5 | Before | Note which pages are deliberately being removed | A 404 you chose is fine; one you did not is not
6 | During | Deploy redirects at the same time as the new site
7 | During | Keep the old sitemap available for a fortnight | It helps the crawler find the redirects
8 | During | Submit the new sitemap
9 | After | Crawl the new site and check for 404s and chains | Within 24 hours
10 | After | Check the top 20 pages by traffic resolve correctly | Do these by hand
11 | After | Watch coverage and rankings weekly for six weeks | Recovery is normal for a fortnight; a month is a problem
12 | After | Compare against the baseline from task 1
Tasks 3 and 4 are where migrations are won. Everything else is execution.