## Capacity
Fill this in before the planning meeting, not during it.
Person | Days in sprint | Leave | Meetings % | Hours available
A. Whitlock | 10 | 1 | 20%
R. Osei | 10 | 0 | 30%
M. Farah | 10 | 2 | 20%
Meetings percentage is the honest part. A team that says 0% is planning to work late.

## Backlog
What could go in. Ordered, estimated, and not yet promised.
Item | Estimate (h) | Priority | Owner | In sprint
Import mapping for CSV | 12 | High | A. Whitlock | Yes
Retry on failed webhook | 6 | High | R. Osei | Yes
Export to Sheets | 16 | Medium |  | No
An item with no estimate cannot be committed to. Estimate it or leave it out.

## Commitment
Formulas. Committed hours against hours available.
Measure | Hours
Available
Committed
Headroom
Negative headroom is not ambition, it is a plan to miss.